## Feuil1
Level of the indicator
Determinant | English | French | Indicator | Responsable | Progress (COMPLETED/IN PROGRESS/TO BE DONE/PROBLEM) | IRIS | Communes | Départements | Régions | Data available (YES/NO) | Problems with the data (YES/NO) | If there are problems, explain the problem: | Additional notes |  | Questions for ECOLAB
Determinant 1 | Air Quality | Qualité de l'air | Nombre moyen de jours supérieur ou égal à mauvais pour la qualité de l'air par IRIS | Jade | Problem |  |  |  | x | No |  | No access to ATMO (requires credentials for access to BDD) as request for API and WFS stream do not work | Have constructed station-level data points from GEOD'AIR dataset | API approach attempted into QGIS - lack of computational power and good quality of data - cannot be converted into a datasheet and extracted this way | Highest spatial resolution of data is station-level, so what radius should be around each station should be used to scale up to IRIS?
|  |  | Indicateur ozone: SOMO 35 | Alfonso / Jade | Problem |  |  |  |  | YES / NO |  |  | Have constructed station-level data points from GEOD'AIR dataset |  | Highest spatial resolution of data is station-level, so what radius should be around each station should be used to scale up to IRIS?
|  |  | Concentration annuelle moyenne des PM2.5 de l'année 2018 | Alfonso / Jade | Problem |  |  |  |  | YES / NO | YES
|  |  | Emissions atmosphérique | Jade | Problem |  |  |  |  | NO | Yes | INS link does not work - as outlined in cahier des charges
| Air Quality - Biodiversity | Qualité de l'air - Biodiversité | Risque d'allergies au pollen | Jade | Problem |  |  |  |  | No | Yes | Form to request for access doesn't work and data set is not available on website: https://www.pollens.fr/reports/database | Website shows cartography for day with information required but no way to look at historical data to hard code
|  |  | Risque d'allergies á l'ambroisie | Jade | Problem |  |  | x | x | No | Yes | No way to access dataset from cartography | Used data in github dated from 2022 |  | To use count by of ambroisies by departement in 2022 (data source: GD4H challenge) as a substitute for this indicator?
Determinant 2 | Water management | Gestion des eaux | Indicateur global annuel de la qualité de l'eau destinée a la consommation humaine selon sa contruction par région pour l'année 2018 | Julian | Problem | x |  |  |  | No | Yes | Zip files do not contain the data base to process information
|  |  | Indicateur qualité des eaux de surfaces | Julian | Problem | x |  |  |  | NO | YES | Data base is not updated (the lastest year for the SIE data base 2015), and the information about how to get the description of the body of water (from the SIE), is no clear. The data "Water stream quality station: physico-chemical status" there is no station code to link with the NAIADES databse. There is no specific information about the chemical tresholds and the links to access data on SIE is unavailable i.e "continental surface water quality measuring station - STQ.
|  |  | Indicateur qualité des eaux souterraines | Julian | Completed | x |  |  |  | YES | NO |  | The aggregated score was calculated. It did not discriminate between cuves and waste storage facility
|  |  | Indicateur risque inondation | Jade | [5 empty] | YES | NO
|  |  | Indicateur sécheresse | Julian | Completed |  |  |  |  | YES | YES |  | Geometry did not include all the zones in France. Only 53 observations
Determinant 3 | Floor quality | Qualité des sols | Proximité des sites et sols pollués - indicateur Ineris |  | To do
|  |  | Risque radon | Alfonso (?) | To be done |  |  |  |  | YES | NO
|  |  | Proximité des installations de stockage et de production de déchets dangereux - Indicateur Ineris | Sofia | To do
|  |  | Qualité de la biodiversité du sol | Alfonso (?) | To do |  |  |  |  | NOT SURE |  |  | I have looked at some possible data for this indicator, there is a map that I'm not sure how to access the data that quantify the soil biodiversity in France by looking at ADN in samples of soil : https://www.gissol.fr/donnees/cartes/1440-1440
Determinant 4 | Biodiversité | Invasion des mosquites tigres | A definir | Sofía | In progress |  |  |  | x | YES |  | Still don't know how to define the indicator
|  | Tiques |  | Sofía | Problem |  |  |  |  | NO |  | The document says that we should ask for this information
|  | Quantités de pesticides achetés par commune, pondérées par leurs toxicités | Quantity of pesticides by classification and postal code | Sofia | Completed |  |  |  | x | YES | NO | I couldn't ponderate by the toxicite since the classification method is different, however I think it works by dividing the type of pesticides and not ponderating | Source: https://www.data.gouv.fr/fr/datasets/achats-de-pesticides-par-code-postal/
Determinant 5 | Temperature | Temperature | Taux de surface végétale a partir de Copernicus | Sofía | Problem |  |  |  |  | YES | YES | The website cancells the download
|  |  | Taux de couvert forestier á partir de Copernicus | Alfonso | Completed | x | x | x | x | YES | NO |  | Practically the indicator is ready, now I have to think on a way to display it (interactive map) and maybe boxplot or other graphs options... before continuing with other satellite datas
|  |  | Taux de surface imperméabilisée | Sofía | Completed |  | x | x | x
|  |  | Nombre annuel de jours chauds, nuit chaudes, vagues de chaleur, vagues de froid | Sofía | Problem |  | x | x | x | NO | YES | Apparently there is no database, looks like if we want to get the information we will have to do webscrapping for all the communes. | https://meteofrance.com/climadiag-commune https://www.drias-climat.fr/commande
Determinant 6 |  | Pollution lumineuse/luminosité | Radiance | Alfonso | Completed | x | x | x | x | YES | NO
|  |  | Radiance | Jade | Problem |  |  |  |  | YES | YES | Satellite images are recognised as insecure downloads by my PC
Determinant 7 |  | Environnement sonore | Part de la surface soumisea un niveau de bruit superieur a 62 db provenant des infraestuctures routieres le jour | Jade | [5 empty] | NO | YES | N/A - should have been provided by ECOLAB (CEREMA)
|  |  | Taux de population soumis a un niveau de bruit superieur a 62 db provenant des infraestructures routieres la nuit | Jade | [5 empty] | NO | YES | N/A - should have been provided by ECOLAB (CEREMA)
Determinant 8 |  | Champs électromagnétiques | Exposition aux ondes | Sofia | Problem |  |  |  |  | YES | YES | When the option to download is pressed the following appear: This Connection is Invalid. SSL certificate expired. | https://www.data.gouv.fr/fr/datasets/statistiques-sur-les-antennes-mobiles-en-france/#/resources
|  |  | Ligne a haute et tres haute tension: controle | Sofia | Problem | [6 empty] | Apparently there is no database, looks like if we want to get the information we will have to do webscrapping for all the communes. | https://cem-mesures.fr/
Determinant 9 | Security | Sécurité | Coups et blessures volontaires (taux) 2022 | Maela | Completed |  | x | x | x
|  |  | Vols sans violence contre des personnes (taux) 2022 | Maela | Completed |  | x | x | x
|  |  | Cambriolages de logement (taux) 2022 | Maela | Completed |  | x | x | x
|  |  | Usage de stupéfiants (taux) 2022 | Maela | Completed |  | x | x | x
Determinant 10 | Remoteness | Eloignement | Part de la population éloignée des équipements intermédiaires, 2021 | Maela | In progress | [6 empty] | Time taken to calculate isochrones = 1 night for 2,000 isochrones -> problem = 36,000 communes and 15,000 IRIS + 4 indicators with different isochrones (6 minutes, 12 minutes, 15 minutes, 21 minutes)
|  |  | Part de la population éloignée des équipements de proximité, 2021 | Maela | Problem | [6 empty] | Time taken to calculate isochrones = 1 night for 2,000 isochrones -> problem = 36,000 communes and 15,000 IRIS + 4 indicators with different isochrones (6 minutes, 12 minutes, 15 minutes, 21 minutes)
|  |  | Part de la population éloignée des équipements supérieurs, 2021 | Maela | Problem | [6 empty] | Time taken to calculate isochrones = 1 night for 2,000 isochrones -> problem = 36,000 communes and 15,000 IRIS + 4 indicators with different isochrones (6 minutes, 12 minutes, 15 minutes, 21 minutes)
| Unemployment rate | Taux de chômge | Part de chômeurs de 15 à 64 ans en 2020 (sur personnes actives) | Maela | completed | x | x | x | x
| Cycling rate | Taux de cyclabilité | Taux de cyclabilité | Maela | In progress |  | x | x | x
Determinant 11 | Rate of accessible sports facilities | Taux d'infrastructures sportives accessibles |  | Maela | In progress | [6 empty] | Time taken to calculate isochrones = 1 night for 2,000 isochrones -> problem = 36,000 communes and 15,000 IRIS + 4 indicators with different isochrones (6 minutes, 12 minutes, 15 minutes, 21 minutes)
Determinant 12 | Part de la population dépendante de la voiture pour accèder aux commerces | Part de la population dépendante de la voiture pour accèder aux commerces |  | Maela | In progress | [6 empty] | I'm waiting for an administrator to validate my access to Géodip
| Percentage of organic plots | Pourcentage de parcelles bio | Part des surfaces agricoles biologiques en conversion dans la surface agricole biologique totale (%) 2020 | Maela | Completed |  | x | x | x
Determinant 13 | Percentage of households in a situation of energy vulnerability | Part de ménages en situation de vulnérabilité énergétique |  | Maela | In progress |  |  |  |  | YES | YES
| Over-occupation | Suroccupation du logement | Part des résidences principales (hors studio de 1 personne) suroccupées 2020 | Maela | Completed | x | x | x | x
Determinant 14 | Share of poor households | Part de ménage pauvre | Taux de pauvreté | Maela | Completed |  | x | x | x
| Social disadvantage | Défaveur social | Indicateur Fdep | Maela | Completed | x | x | x | x
| Generational mix | Mixité générationnelle | Part des pers. âgées de - de 25 ans 2020 | Maela | Completed | x | x | x | x
|  |  | Part des pers. âgées de 25 à 64 ans 2020 | Maela | Completed | x | x | x | x
|  |  | Part des pers. âgées de 65 ans ou + 2020 | Maela | Completed | x | x | x | x
| Social mix | Mixité sociale | Part des ouvriers au lieu de travail en 2020 | Maela | Completed | x | x | x | x
|  |  | Part des employés au lieu de travail en 2020 | Maela | Completed | x | x | x | x
|  |  | Part des cadres au lieu de travail en 2020 | Maela | Completed | x | x | x | x

## Copie de Feuil1 (hidden)
Level of the indicator
Determinant | English | French | Indicator | Responsable | Progress (COMPLETED/IN PROGRESS/TO BE DONE/PROBLEM) | IRIS | Communes | Départements | Régions | Data available (YES/NO) | Problems with the data (YES/NO) | If there are problems, explain the problem: | Additional notes
Determinant 1 | Air Quality | Qualité de l'air | Nombre moyen de jours supérieur ou égal à mauvais pour la qualité de l'air par IRIS | Jade | [5 empty] | No |  |  | In progress, waiting for approval for API: https://www.atmo-france.org/article/atmo-data-un-acces-unique-aux-donnees-produites-par-les-aasqa | API approach attempted into QGIS - lack of computational power and good quality of data - cannot be converted into a datasheet and extracted this way
|  |  | Indicateur ozone: SOMO 35 | Alfonso / Jade | To be done |  |  |  |  | YES / NO |  |  | Geospatial data are available so everything should be fine, like all the other spatial data however, we will not use a 4kmx4km resolution but iris/communes/départements/region scales instead
|  |  | Concentration annuelle moyenne des PM2.5 de l'année 2018 | Alfonso / Jade | To be done |  |  |  |  | YES / NO | YES | We only have one data point per station, 147 overall corresponding to some cities (while there are around 35 000 cities in Fr) - doing a mean per region might be wrong so we will only have the concentration per city, with loads missing
|  |  | Emissions atmosphérique | Jade | [5 empty] | NO | Yes | INS link does not work - as outlined in cahier des charges
| Air Quality - Biodiversity | Qualité de l'air - Biodiversité | Risque d'allergies au pollen | Jade | [5 empty] | No | Yes | Form to request for access doesn't work and data set is not available on website: https://www.pollens.fr/reports/database | Website shows cartography for day with information required but no way to look at historical data to hard code
|  |  | Risque d'allergies á l'ambroisie | Jade | [6 empty] | Yes | Same problem | Same problem
Determinant 2 | Water management | Gestion des eaux | Indicateur global annuel de la qualité de l'eau destinée a la consommation humaine selon sa contruction par région pour l'année 2018
|  |  | Indicateur qualité des eaux de surfaces | Julian | In progress |  |  |  |  | NO | YES | Data base is not updated (the lastest year for the SIE data base 2015), and the information about how to get the description of the body of water (from the SIE), is no clear. The data "Water stream quality station: physico-chemical status" there is no station code to link with the NAIADES databse. There is no specific information about the chemical tresholds and the links to access data on SIE is unavailable i.e "continental surface water quality measuring station - STQ.
|  |  | Indicateur qualité des eaux souterraines | Julian
Indicateur risque inondation
|  |  | Indicateur sécheresse | Julian
Determinant 3 | Floor quality | Qualité des sols | Proximité des sites et sols pollués - indicateur Ineris
|  |  | Risque radon | Alfonso (?) | To be done |  |  |  |  | YES | NO
Proximité des installations de stockage et de production de déchets dangereux - Indicateur Ineris
|  |  | Qualité de la biodiversité du sol | Alfonso (?) | To be done |  |  |  |  | NOT SURE |  |  | I have looked at some possible data for this indicator, there is a map that I'm not sure how to access the data that quantify the soil biodiversity in France by looking at ADN in samples of soil : https://www.gissol.fr/donnees/cartes/1440-1440
Determinant 4 | Biodiversité | Invasion des mosquites tigres | A definir | Sofía | In progress |  |  |  | x | YES |  | Still don't know how to define the indicator
|  | Tiques |  | Sofía | Problem |  |  |  |  | NO |  | The document says that we should ask for this information
|  | Quantités de pesticides achetés par commune, pondérées par leurs toxicités | Quantity of pesticides by classification and commune | Sofia | Completed |  | x | x | x | YES | NO | I couldn't ponderate by the toxicite since the classification method is different, however I think it works by dividing the type of pesticides and not ponderating | Source: https://www.data.gouv.fr/fr/datasets/achats-de-pesticides-par-code-postal/
Determinant 5 | Temperature | Temperature | Taux de surface végétale a partir de Copernicus | Sofía | Problem |  |  |  |  | YES | YES | The website cancells the download
|  |  | Taux de couvert forestier á partir de Copernicus | Alfonso | Completed | x | x | x | x | YES | NO |  | Practically the indicator is ready, now I have to think on a way to display it (interactive map) and maybe boxplot or other graphs options... before continuing with other satellite datas
|  |  | Taux de surface imperméabilisée | Sofía | Completed (almost) |  | x | x | x
|  |  | Nombre annuel de jours chauds, nuit chaudes, vagues de chaleur, vagues de froid | Sofía | Problem |  | x | x | x | NO | YES | Apparently there is no database, looks like if we want to get the information we will have to do webscrapping for all the communes. | https://meteofrance.com/climadiag-commune https://www.drias-climat.fr/commande
Determinant 6 |  | Pollution lumineuse/luminosité | Radiance | Alfonso (?) | [5 empty] | NOT SURE |  |  | I tried accessing the data, I didn't manage to do it but at least they exist, I just have to find the way to download them which is not obvious
Radiance
Determinant 7 |  | Environnement sonore | Part de la surface soumisea un niveau de bruit superieur a 62 db provenant des infraestuctures routieres le jour
Taux de population soumis a un niveau de bruit superieur a 62 db provenant des infraestructures routieres la nuit
Determinant 8 |  | Champs électromagnétiques | Exposition aux ondes | Sofia | Problem |  |  |  |  | YES | YES | When the option to download is pressed the following appear: This Connection is Invalid. SSL certificate expired. | https://www.data.gouv.fr/fr/datasets/statistiques-sur-les-antennes-mobiles-en-france/#/resources
|  |  | Ligne a haute et tres haute tension: controle | Sofia
Determinant 9 | Security | Sécurité | Coups et blessures volontaires (taux) 2022 | Maela | Completed |  | x | x | x
|  |  | Vols sans violence contre des personnes (taux) 2022 | Maela | Completed |  | x | x | x
|  |  | Cambriolages de logement (taux) 2022 | Maela | Completed |  | x | x | x
|  |  | Usage de stupéfiants (taux) 2022 | Maela | Completed |  | x | x | x
Determinant 10 | Remoteness | Eloignement | Part de la population éloignée des équipements intermédiaires, 2021 | Maela | Completed |  | x | x | x
|  |  | Part de la population éloignée des équipements de proximité, 2021 | Maela | Completed |  | x | x | x
|  |  | Part de la population éloignée des équipements supérieurs, 2021 | Maela | Completed |  | x | x | x
| Unemployment rate | Taux de chômge | Part de chômeurs de 15 à 64 ans en 2020 (sur personnes actives) | Maela | Completed | x | x | x | x
| Cycling rate | Taux de cyclabilité | Taux de cyclabilité | Maela | Completed |  | x | x | x
Determinant 11 | Rate of accessible sports facilities | Taux d'infrastructures sportives accessibles |  | Maela | In progress
Determinant 12 | Part de la population dépendante de la voiture pour accèder aux commerces | Part de la population dépendante de la voiture pour accèder aux commerces |  | Maela | In progress
| Percentage of organic plots | Pourcentage de parcelles bio | Part des surfaces agricoles biologiques en conversion dans la surface agricole biologique totale (%) 2020 | Maela | Completed |  | x | x | x
Determinant 13 | Percentage of households in a situation of energy vulnerability | Part de ménages en situation de vulnérabilité énergétique |  | Maela | Completed |  |  |  |  | YES | YES | I'm waiting for an administrator to validate my access to Géodip
| Over-occupation | Suroccupation du logement | Part des résidences principales (hors studio de 1 personne) suroccupées 2020 | Maela | Completed | x | x | x | x
Determinant 14 | Share of poor households | Part de ménage pauvre | Taux de pauvreté | Maela | Completed |  | x | x | x
| Social disadvantage | Défaveur social | Indicateur Fdep | Maela | Completed | x | x | x | x
| Generational mix | Mixité générationnelle | Part des pers. âgées de - de 25 ans 2020 | Maela | Completed | x | x | x | x
|  |  | Part des pers. âgées de 25 à 64 ans 2020 | Maela | Completed | x | x | x | x
|  |  | Part des pers. âgées de 65 ans ou + 2020 | Maela | Completed | x | x | x | x
| Social mix | Mixité sociale | Part des ouvriers au lieu de travail en 2020 | Maela | Completed | x | x | x | x
|  |  | Part des employés au lieu de travail en 2020 | Maela | Completed | x | x | x | x
|  |  | Part des cadres au lieu de travail en 2020 | Maela | Completed | x | x | x | x